## Gantt Chart
Part III Project - Semester 1
Task | Start Date | End Date | Duration
Research
Research Lua | 2020-10-05 | 2020-10-21 | 16
Research DSLs | 2020-10-15 | 2020-11-27 | 43
Evaluate and categorise various addons | 2020-10-21 | 2020-12-03 | 43
Create and release Lua questionnaire | 2020-11-05 | 2020-12-03 | 28
Analyse questionnaire results | 2020-12-03 | 2020-12-08 | 5
Planning
Create a list of requirements | 2020-11-27 | 2020-12-08 | 11
Select an appropriate compiler | 2020-11-27 | 2020-12-08 | 11
Define a formal type system | 2020-12-08 | 2021-01-14 | 37
Define the program semantics | 2020-12-08 | 2021-01-14 | 37
Min | 44109
Max | 44210